## RACI
| Critical Activity | Project Manager | Lead Developer | Developer 1 | Developer 2
Administration | Schedule and conduct group meetings | R | C | C | C | KEY | R = Responsible | Responsible for performing the task (ie. the actual person doing the work to complete the task).
| Project implemetation artifact collection and recording | R | C | C | C |  | A = Accountable | Ultimately accountable for the task being done in a satisfactory manner. The accountable person must sign-off the work that the Responsible person produces.
| Establish priorities for ongoing support, maintenance, critical issues and enhancement of the application | A | R | A | A |  | C = Consulted | Team members whose input is used to complete the task. Communication with these members will be 2-way in nature.
| Manage scope, resources and issues related to project management | R+A | R | A | A |  | I = Informed | Team members who are informed as to the status of the task. Communication with these members will be 1-way in nature.
| Project visual design and presentation preparation | R | A | A | A
| Project porposal | R+A | R+A | R+A | R+A
Implementation process | Defining Resources for Data Collection | R | C | A | C
| Keywords List Creation | C | R | A | C
| Automatic Script Development and Scheduling | R | R | C | C
| Classification of Collected Data for Risk Assessment | A | C | R | C
| Data Pre-processing and Vectorization | R | R | A | C
| Clustering and Interpretation | C | R | C | A
| Evaluation | R | C | A | R